## Dashboard
Legacy Ancillary Systems Integrations | Point Person(s) | Target Completion Date | TEST Environment Status | PROD Environment Status | Notes
CCC Apply - Domestic Applications | Dale/Jeff/Bob Lane | 2013-02-14 | Complete | Complete
EDConnect | Chuck Pomeroy | 2013-03-01 | Complete | Complete | Need UC4 file transfer implemented.
CourseWorks (Bookstore) | Chuck Pomeroy | 2013-03-15 | Complete | Complete | 9/26/2013 - The interface/extract is completed. Just waiting on D. Colley to finish Spring Schedule so we can execute the process.
Lancercard ID Card | Dale Pittman CCI (vendor) | 2013-04-18 | n/a | Complete | Completed on 6/26/13
ParScore | Jeff Laun | 2013-04-30 | In Progress… | In Progress…
ParTest | Jeff Laun | 2013-04-30 | In Progress… | In Progress…
CI Track - Lab Tracking | Roger Chung | 2013-06-01 | n/a | Complete | 8/14/13 - the last of the 28 labs are being worked on this week and next week and will be finished by 8/23/2013 8/22/13 Work is complete, still deploying new stations and fine tuning the access JL
25Live (Resource 25, Schedule 25) | chuck Pomeroy Roger Chung | 2013-06-28 | Complete | Complete | Completed. Released to David Colley who is waiting for user training.
Kronos Workforce Mangement | Jeff Laun | 2013-06-30 | n/a | Complete | 8/22/2013 - Extracts done for Maggie, she requests new updates monthly. JL
Canvas - Batch Data Integration | Jeff Laun | 2013-07-01 | n/a | Complete | Hourly loads are being executed.
WMS Sync (hosted Library system) | Jeff Laun | 2013-07-01 | n/a | Complete
Blackboard Mobile (PCC mobile app for class schedule) - daily | Jeff Laun | 2013-07-01 | n/a | Complete
VoiceThread (extract) – some sort of faculty/student social networking app - daily | Jeff Laun | 2013-07-01 | n/a | Complete
Banner-to-LACOE Interface (Finance) - Student Drop Refunds | Dale Pittman (Bob Lane) | 2013-07-10 | n/a | In Progress… | 9/26/2013 - currently sending both student refunds and commercial warrants. Need to move from Bob's desktop machine to the server pending final testing. 98% complete--finalizing documentation. 8/14/13 - we need to do a current review of the process. There are some manual steps required, but some initial student refunds have been completed successully.
LACOE-to-Banner Interface - eRegister (Finance) | Dale Pittman (Bob Lane) | 2013-07-31 | n/a | n/a | 9/26/2013 - team determined that this interface is no longer needed. 6/26 - Bob Lane and Jeff Laun will be assigned to develop this interface.
CalGrant Enrollments extract | Paul V. | 2013-08-01 | n/a | Complete | 9/26/2013 - Extract portion finished.
CalGrant GPAs extracts | Paul V. | 2013-08-01 | n/a | Complete | 9/26/2013 - Extract portion finished.
Sequoia <-> Banner interface for financial aid (grants/loans) for books - $400 | Jeff Laun Rob Tirapelle | 2013-08-01 | n/a | Complete
Point-of-Sale (Bookstore) | Dale Pittman Chuck Pomeroy | 2013-08-16 | n/a | Complete
ClassClimate (or possibly new product) | Jeff Laun | 2013-08-30 | n/a | In Progress… | 9/26/2013 - class load is done, but enrollment is still pending
Photo Materials Checkout | Dale Pittman Jeff Laun | 2013-09-01 | Complete | Complete | 9/26/2013 - Interim integration is complete. Will be replaced by a new system that is to be determined.
Paperless (DSP&S contact recording) | Jeff Laun | 2013-10-01 | n/a | Complete | 9/26/2013 - Banner import of disability codes is finished. New contact and course information will no longer be supported (Banner will be used). The tab will only be used to reference historical data.
LACOE-to-Banner Interface (Finance) - Commercial Warrants | Dale Pittman (Bob Lane) | 2013-10-15 | n/a | In Progress… | 9/26/2013 - 98% complete….pending final testing and minor issue resolution and moving into production and documentation. 8/14/13 - development in progress. Still some issues related to source data that we are working through.
eLumen | Jeff Laun | 2013-10-31 | n/a | In Progress… | 9/26/2013 - extract from Banner is complete. The eLumen team is updating eLumen values based on the updated catalog subject and course number information in the Banner extract.
CCC Apply - International Applications | Dale/Jeff/ Lee McDonald | 2013-10-31 | In Progress… | In Progress… | 9/26/2013 - Dale contacted Lee McDonald to confirm this is still needed. 8/14/13 - Dale waiting on a reply from Lee McDonald
LACOE-to-Banner Interface (HR/Payroll) | Dale Pittman | 2013-10-31 | In Progress… | In Progress… | 9/26/2013 - Bob waiting to hear from Marie. 6/26 - will be assigned to Bob Lane
SARS*GRID | Chuck Pomeroy | 2013-11-15 | In Progress… | In Progress… | 9/26/2013 - upgrades pending, this will become urgent soon. 7/26/2013 - Chuck did not have a target completion date. 6/25/2013 - Chuck is on point for custom solution implementation.
ParkingPlus Integration with SSB | Rowen Garcia | 2013-11-15 | n/a | In Progress… | 9/26/2013 - using interim codes that need to be updated when HR is loaded (need to point to HR tables). Would like to include proper employee code for card. 8/14/2013 - completed on 8/2/2013
eTranscripts System | Roger Chung | 2013-11-30 | In Progress… | In Progress… | 9/26/2013 - waiting on Banner production transcript (evisions), which should be completed by 10/31/2013
Clean Address for INB/SSB (GOAMATCH/PPAIDEN/SPAIDEN/RNANA14?/SOAIDEN?) | Robert Tirapelle Jeff Laun | 2013-12-01 | n/a | In Progress… | 9/26/2013 - Rob Tirapelle will do the Clean Address server component install. Jeff Laun will do the DB integration.
WebCMS (by ITPI) | Jeff Laun | 2013-12-31 | n/a | In Progress… | 8/20/13 Met with Pedro of WebCMS, he will be giving me specs and sample code that Mt Sac uses. 6/26 - ITPI has developed a WebCMS-to-Banner sqlloader that Jeff Laun will implement.
Financial Aid - Work Study | TBD
New System Integrations | Point Person(s) | Target Completion Date | TEST Environment Status | PROD Environment Status | Notes
Banner Enterprise Identity Services (BEIS) | Russell Wright | 2013-03-01 | Complete | Complete
Central Authentication Service (CAS) for INB and SSB | Russell Wright | 2013-04-09 | Complete | Complete
TouchNet Payment Gateway | Rowen Garcia Antonio Trepesowsky | 2013-05-01 | Complete | Complete | The Banner DB components were setup and successfully tested in TEST on 4/26.
Add pay classes to ADAP configuration | Russell Wright | 2013-05-03 | Complete | Complete
Active Directory Account Provisioning (ADAP) | Russell Wright | 2013-07-01 | Complete | Complete
Canvas Single Sign-on via CAS | Russell Wright Robert Tirapelle | 2013-07-01 | Complete | Complete | Production will be enabled as part of the portal go-live checklist on 7/11/2013
Outlook Web Access Single Sign-on (via GCF) from LancerPoint portal | Russell Wright | 2013-07-01 | Complete | In Progress… | 8/24/2013 - An additional IP address needs to be added to the network so that OWA can be directed from the Internet through the F5 load balancer. Completion date TBD.
Google Mail for Students (automated account provisioning and single sign-on) | Russell Wright Robert Tirapelle | 2013-07-11 | n/a | Complete | Preferred e-mail notifications will be enabled as part of the portal go-live checklist on 7/11/2013
CAS Integration for DegreeWorks | Russell Wright | 2013-10-31 | In Progress… | In Progress… | Added on 8/14/2013
CAS Integration for Rave Alerts | Russell Wright | 10/31/0213 | In Progress… | In Progress… | Added on 8/14/2013
Person Load / Data Integrationfor Rave Alerts | Jeff Laun Chuck Pomeroy (UC4) | n/a | n/a | In Progress… | 9/26/2013: Jeff has created a batch process that is completed and that will be used instead of the Rave Alerts near-real-time components. This needs to be added to UC4. Added on 8/14/2013

## Integration - In Scope
Application System Name | Status | Source | Areas Directly Supported | Functional Description | Point Person | Category | Rick's Comments | Type of Integration | Frequency | SSO? | Link? | Account Dependency | Date Required | Priority | Estimate (hours) | When Required? | Notes
CCC Apply - Domestic Applications | Completed | XAP Corporation | Admissions and Records | Online application system for domestic (non international) students [Interfaces to the SIS] | Dale/Jeff/Bob Lane | 3 | "Community Source" | Custom ETL | Daily | N | N | N | 2013-02-14 | High | n/a | By February 28, 2013 for domestic students. | Being implemented by third party - Lee McDonald
EDConnect |  | Federal Government | Financial Aid Office | Electronic transfer system for EDExpress | Chuck Pomeroy | 3 | Banner Financial Aid | ETL (2-way). Banner has a standard interface. FTP security important. | On-demand several times/day. |  |  |  | 2013-03-01 | High | n/a | By March 2013 | 2-way transfer of files and imported into Banner. There are approximately 30 types of files. Both the extract and import jobs are standard. Felicia needs to be trained (by Chuck) on how to transfer files securely. Should be set up on severeal other PCs (TBD)
CourseWorks |  | Follette | Bookstore | Textbook management system [Interfaces to Bookstore Point-Of-Sale System] | Chuck Pomeroy | 3 | Community Source -- See Brandman University | Data. One-way out of Banner. Just need to define extract requirements. Can use existing extract requirements from SIS. | Once/semester (after schedule frozen) |  |  |  | 2013-03-15 | Medium | 8 | Required for Summer term - March 2013. Schedule will be stablized by ~3/25/2013 4/24: Fall 2013 was done out of legacy system. This extract needed for Spring 2014 book buy. | Conf call scheduled for 4/26
Lancercard ID Card |  | CCS | All areas Students | Links to both Student Records System and PCCHRS System to validate person prior to authorizing the creation of a student or staff ID card; the student must be enrolled in one of the current semesters to obtain a LancerCard ID card [Interfaces to the SIS] [Interfaces to LACOE-HRS via PCCHRS] Contact: Taylor Cole, CI Solutions Card Integrators Corporation Corporation Tel (800) 599-7385 ext. 536 www.cardintegrators.com | CCI (vendor) | 3 | "Community Source" for CI Solutions. Also, BRM now supports Banner storage of ID Photo. NOCCCCD currently has an upload process available. | Needs to pull Banner registration information from Banner. This application needs to be a real-time DB query (ODBC). Application may need to be updated to use Oracle thin driver for DB connection. Table to query: SFRSTCR card generates for active employees and for registered students. PCC has existing maintenance agreement with CCI. | real-time |  |  |  | 2013-04-18 | Critical | ? | Required by March 2013 (for April 18th registration period) for Students and as part of HR implementation for employees. | Dale will work with CI Solutions in order to update the system's ODBC connection for the Banner DB: Test Banner DB: Hostname: bandbtest.pasadena.edu Listner Port: 1521 DB SID: TEST DB Service Name: TEST.pasadena.edu Prod Banner DB: Hostname: bandbprod.pasadena.edu Listner Port: 1521 DB SID: PROD DB Service Name: PROD.pasadena.edu Issue: We will not have employees in Banner until HR is implemented unless we populate a custom table that we can use a basis for calculating the EMPLOYEE GORRSQL role. A card will not be generated/issued until PCC sees a registration. Should be in production by 6/26. CITRACK needs select on GORIROL for this to be completed.
AccuPlacer |  | Academic Systems | Student Online Assessment System |  |  | 3 |  | Extract from AccuPlacer uploaded daily and imported into Banner via SRTLOAD. | Daily |  |  |  | 2013-04-26 | High | 8 | Done prior to Student go live. | Extract is configurable by the user. Antonio can configure the extract/load. 4/24: Jeff will work with Antonio on this. 6/21: Replaced by CI Track
ParScore |  | ScanTron | Division Offices Faculty | Automated classroom scoring system | Jeff Laun | 3 | Community Source" ?? | ETL. One-way from Banner into Par*. There is an existing extract from SIS. | Several times / Semester | N |  |  | 2013-04-30 | High | 8 | Beginning Student Go-live
ParTest |  | ScanTron | Division Offices Faculty | Automated classroom testing system | Jeff Laun | 3 | Community Source" ?? | ETL. One-way from Banner into Par*. There is an existing extract from SIS. | Several times / Semester | N |  |  | 2013-04-30 | High | 8 | Beginning Student Go-live
SARS*GRID |  | SARS Software Products | Student and Learning Services Other areas | Appointment and initial service request system Includes SARS*Call [Interfaces to the SIS] | Dale / Jeff | 3 | SARS-Call at end-of-life; SARS moving to SARS-MSGS; PCC currently taking no action since SAR*Call is longer in use. | a daily extract to be developed Jeff | Daily | N | N | N | 2013-05-01 | High | 0 | Required by the time we start accepting student conferences for summer. March 2013 | 4/24: Mark decided that the SARS/Banner integration service will not be implemented. Rio Hondo implemented a custom process that will be implemented at PCC. He will review implementation details with Jeff Laun.
eLumen |  | eLumen | Instructional Divisions Institutional Planning and Research Faculty | Student Learning Outcomes management, tracking, and reporting system. Feed of enrollment data | Jeff Laun | 3 | Retain and integrate with Banner | ETL. One-way from Banner to eLumen | Twice/semester |  |  |  | 2013-05-31 | Medium | 8 | May 31, 2013 | In the future these might come out of ODS in order to minimize hitting the PROD database directly.
25Live -Resource25 -Schedule25 | In Progress | CollegeNET | Facilities Use Police and Safety Facilities Other areas with scheduling needs | Room Event and Scheduling System [Iinterfaces to the SIS] | Chuck Pomery Jeff Laun | 3 | CollegeNet Maintains Banner Interface. Two-way: we feed schedule data and it returns schedule data with a room attached. Batch-driven. | Direct data connection into Banner | Real-time |  |  |  | 2013-06-01 | Low | n/a | 1/31: Needed for Spring 2014 (build starts in Sept. 2013). 4/26: Summer 2013 | Event scheduling not currently done through R25. Jeff is managing it. It is not currently live, so it represents new functionality. There is a standard Banner interface. 4/24/13: Rowen completed the setup of the Banner components. When the application is installed/configured, we will need to test. Banner will initially be used to schedule rooms. Eventually, Schedule25 will be used to actually book the rooms.
CI Track - Lab Tracking |  | CI Track Software | Student lab tracking | Student lab tracking | Jeff Laun. Roger Chung | 3 |  | Data. Need to review CI track integration components when Dale receives them. | TBD | N |  |  | 2013-06-01 |  |  | For Summer 2013 term (June 23) | The first time a user swipes into CI track it needs to update their registration. It needs to register them in a class. Some times the lab is a self-help lab, so swiping in requires registration in that lab. Existing registration swipes are not passed back to Banner--tracked only in CI Track 4/24: CI Track provides integration components that we will need to integrate. Estimate that Dale will have the components by 5/1. Business process for enrolling students in tutoring needs to be developed (giving users permission to enroll in tutoring classes (should have a CRN?)). 6/25 - Roger reported that the pull of course data from Banner is working and 6 of the 20-something labs are set up and using CI Track Lab Tracking. The remaining labs will be done for Fall 2013.
eTranscripts System |  | XAP Corporation | Admissions and Records | Electronic transcripts systems for transmittal and receipt of student transcript information with other eTranscript partners [Interfaces to the SIS] | Dale/Jeff | 3 | "Community Source" available from NOCCCD | ETL (EDI 189 and XML formats supported by Banner). Need to decide which. Part of Banner baseline as long as adheres to above formats. | On-demand and batch. |  |  |  | 2013-06-15 | High | 72h | End of Summer term 2013. Outbound must be completed before end of June 2013 to qualify for grant funds. | Not in production today. Decision to implement pre-dated Banner selection. There are two exchange clearinghoues (one in CA (eTrans) and one in Texas. Antonio handles the Banner configuration. The CALB version does not use a student level code (because there is only one CCC level (CR)). eTrans does not have a level indicator. Need a small mod to accommodate the student level property. Transcript data (not the image) is transferred. Get from Lee McDonald. 4/25 (Dale): are contracted with Credentials for Parking but NOT diploma. 4/25 (Antonio): Address type is ‘PR’ and e-mail type is ‘CAMP’
Canvas |  | Canvas | Students/Faculty | Learning Management System | Robert Tirapelle | 3 | Pending interface development of Canvas interface | Single Sign-on via CAS | Real-time | Y | N | Y | 2013-07-01 |  |  | Portal go-live
CalGrant Enrollments extract |  | Banner |  |  | Paul V. | 3 |  | 1-way data integration: Grant extract GPA extract Once CalGrant approves and sends back awards, the data needs to be imported into Financial Aid. | On-demand. Typically once/semester. |  |  |  | 2013-08-01 | High | TBD | Required by August 2013. For Summer, enrollments will come out of Banner and grades (GPA) will come out of legacy. | 4/24: discuss with Antonio - support for defining extract.
ClassClimate (in deployment phase for fall 2011 teacher evaluations by students) |  | Scantron | Institutional Planning and Research Online (Distance) Education Enrollment Management | Online and batch survey system used to evaluate different aspects of the college's services, including Instruction, Student and Learning Services, and administration [Interfaces to the SIS] | Jeff Laun | 3 | CalB & International Surevey Engine | Data. One-way out of Banner. Just need to define extract requirements. Can use existing extract requirements from SIS. | On-demand. Typically once/semester. |  |  |  | 2013-08-30 | High | 8 | For Fall (no evaluations during Summer) | Antonio and provide SME information.
WebCMS |  | ITPI | Curriculum Instruction Office All Faculty | Course Management System Maintains curriculum for college from time of course proposal to acceptance by Board (Interfaces to Student Records) [Interfaces to the SIS] | Jeff Laun | 3 | "Community Source" or implementation of Banner Course Catalog, BDMS, plus Workflow | ETL. Once a course has been approved, we may need a push into Banner with the required course information. Could be implemented as a workflow? 4/24. No "integration" per se. Creating courses in Banner will be done manually. A business process needs to be created to support this activity. | Annually |  |  |  | 2013-09-15 | Low | 24 | for the 2014/15 catalog. | If WebCMS could be extended to include some Banner-required fields, we could simpify the integration. Catalog was configured from WebCMS, so a lot of it is already in place, but there are some pieces missing that we will need to detail with Anotnio. If a faculty wants to create a brand new course, it is developed/submitted to WebCMS. The finished/approved course needs to be loaded into Banner. 4/24: Creating the courses in Banner will be a user activity. business process needs to be defined to support this. 6/26: Vendor (ITPI) has developed a Banner interface that will be implemented.
CalGrant GPAs extracts |  | Banner |  |  | Paul V. | 3 |  | 1-way data integration: Grant extract - Enrollments extract (SSNs) - GPA extract (two files: regular and re-established GPAs) Once CalGrant approves and sends back awards, the data needs to be imported into Financial Aid | On-demand. Typically once/semester. |  |  |  | 8/1/2013 Submission deadlines are Sept and March. | High | TBD | Required by August 2013. For Summer, enrollments will come out of Banner and grades (GPA) will come out of legacy. Chuck in the CA Solution Center is working on scripts to set up the environment. This is necessary, but the front end is not identified yet in this document. Regardless of how awards get entered, this integration is required. | 4/24: discuss with Antonio - support for defining extract.
Canvas |  | Canvas | Students/Faculty | Learning Management System | Jason / Leslie / Jeff | 3 | Pending interface development of Canvas interface | Data | Daily if batch, possibly real-time events. | Y | N | Y | Class loads will begin: 5/10 Student loads will begin: 6/17 |  |  | Summer Term
CCC Apply - International Students Applications (in development) | In Progress | XAP Corporation | Admissions and Records International Students Office | Online application and workflow system for international students [Interfaces to the SIS] | Dale/Jeff/Bob Lane | 3 | "Community Source" | Custom ETL | Near-real time (every 15 minutes) |  |  |  | TBD | High | n/a | By May 2013 (for Fall) | Being implemented by third party - Lee McDonald ISSM training scheduled June 3-5
Kronos Workforce Mangement |  | Kronos | Payroll All served departments | Employee absence and accrual tracking and reporting system [Interfaces to LACOE-HRS via PCCHRS] |  | 3 | Interface or Banner HR Web Time Entry | ETL, 2-way. Uses both schedule data and HRS data. Similar to Facutly Load and Compensation (FLAC). Need faculty ID and section they are teaching in the extract. LDIASSIGN extract may possibly work for this (transition 1) until HR is live and transition 2 (go-live for payroll). | [7 empty] | No later than June 24 (when Summer starts) - fully functional | Kronos being used to: Create assignments for adjuncts Can accrue leaves Currently tracking full-time people (absences, leave, exception time for full-times) Tracking hourlies Positive time keeping (I worked these days) and exception time (I didn't work these days). Will be used through 3 transitions: 1. Kronos now until Finance go-live (July 1) 2. July 1 --> Payroll go-live (mid December, start of pay period) 3. Go-live for Payroll (i.e. the last time we convert data--at this point, we are "live" for HR). Non-instructional time is a lump sum handled in HRS. Time beyond salaried, is overload in HRS. Antonio working with Maggie on this (4/23/2013) 4/24: this is in a holding pattern until HR is in test mode (until we decide on the system of record (LACOE HRS or Banner HR)
Photo |  | In-House | Visual Art and Media Studies | System to handle the check-out functions of equipment for the photo lab [Interfaces to the SIS] | Dale | 3 | Unknown Status | Written in Delphi. Equipment checkout system. If can be done in current system, we may have no integration requirements. May need to pull reg data from Banner. | Once/semester | N | [5 empty] | Summer 2013 if photo classes are being offered for Summer. | If our lab system has resource allocation capabilities, it will replace this system. Will re-examine this mid-Feb, 2013 4/24: potential second module from CI Track. Still being examined.
Point-of-Sale (Bookstore) |  | Sequoia Retail System | Bookstore | Point-of-Sale system for bookstore [Interfaces to the SIS] | Dale and Chuck | 3 | "Community Source" However, do they use both Sequoia and Follette | Extract by student of a loan amount / grant amount for books. | [5 empty] | High | 8 | For Summer term 2013? | This is the basis for the bookstore ordering books for the term. Meeting scheduled for 4/26/2013 with bookstore. 4/24: pending Extended Opportunity Program & Services (EOP&S) / business process discussion.
Sequoia <-> Banner interface for financial aid (grants/loans) for books. |  | Sequoia Retail System | Bookstore |  | Jeff Laun Rob Tirapelle | 3 |  | Affects financial aid book loans / book grants. More discussion needed between Accounting, Bookstore and Financial Aid. More input needed from Mollie, Dale, Antonio and others. | [8 empty] | Beginning week before a term, Banner will be queried to determine if > $400 has been allocated for books. At end of night, bookstore will post back what student has spent and posted as charge to student account. Balance is recalculated and sent back to bookstore. Sequoia developed the interface for this.
WMS Sync (hosted Library system) | done |  | Library | synching Banner students with library patrons |  | 3
Blackboard Mobile (PCC mobile app for class schedule) - daily | done |  |  | Schedule & catalog extract (one-way) |  | 3
VoiceThread (extract) – some sort of faculty/student social networking app - daily | ? |  |  |  |  | 3
DSP&S Paperless System |  | In-house | DSP&S | Workflow Paperless system to securely track DSP&S contacts with students |  | 3 | Banner Student and Ellucian Workflow
Financial Aid - Work Study

## Integration - Out Of Scope
Application System Name | Source | Areas Directly Supported | Functional Desctiption | Point Person | Category | Rick's Comments | Type of Integration | Frequency | SSO? | Link? | Account Dependency | When Required?
Academic Systems CBT | Academic Systems | Mathamatics Division | Computer Based Teaching system used for mathematics classes |  | 1 | Banner Interface not expected/needed
ActionPlanIt (Eliminated) | Data2Info | Student and Learning Services Community Education Center Counseling | Student Educational Planning System [Interfaces to the SIS] |  | 1
ATI*Filer | In-House (originally from commercial company) | Student and Learning Services Community Education Center | Document imaging system Being migrated to Nolij |  | 1 | Ellucian BDMS | 1-time conversion, no ongoing integration.
BlackBoard 9.1 (moving to Canvas) | BlackBoard | Distance Education Students and faculty | Outsourced system to provide Classroom Management System ranging from full on-line instruction to activities or information in support of the classroom Interfaces to the SIS |  | 1 | Pending interface development of Canvas interface
Financial Aid Management System (FAMS) |  | Regent | Financial Aid Office Fiscal Services | Scholarships and Financial System Interfaces to EDExpress and Fiscal for financial aid warrants to students [Interfaces to the SIS] |  | 1 | 1. "Units Extract" Banner extract (Registration units) - Banner -> FAMS (on demand when FinAid asks for it) Testing completed: March 20 Ready for production: April 18 2. payment import FAMS --> Banner Extract FAMS -> Banner for disbursements/refunds April 18th (all interactions with FAMS) Testing completed: March 20 (actually testing on April 2) Ready for production: May 17 (earliest date we would need this) 3. Refunds (not just finaid) dollar amount from Banner --> LACOE If #4 below is in place, this interface not needed to July since GEORGE could send LACOE requests. Testing completed: First week of April (July if #4 below is used) Production Ready: Earliest, April 26 Latest, May 17 4. Banner student data --> GEORGE (financial information) by April 15th. All on in one table in Banner (gurfeed) gurapay (for refunds out of Banner) | [9 empty] | Keeping in a legacy environment until November 2013. No integration required at this time.
Budget | In-House | Business Services and Fiscal Services | District Budget System When the Budget has been adopted, budgeted amounts are transferred into the Fiscal System [Interfaces to the Fiscal System] |  | 1 | Banner Finance
DonorPerfect | DonorPerfect | Foundation | Donor management system |  | 1 | Unknown Status. Could be Banner Advancement Implementation Dale: Stand-alone
DSP&S Paperless System | In-house | DSP&S | Workflow Paperless system to securely track DSP&S contacts with students |  | 1 | Banner Student and Ellucian Workflow
EagleSoft Dental Office System (in deployment phase) | EagleSoft | Health Sciences - Dental Program | Management system for dental offices |  | 1 | Unknown Status Dale: Stand-alone
EDExpress | Federal Government | Financial Aid Office | Financial aid request and dispersal system [Interfaces to FAMS] |  | 1 | No longer used.
EdPlan (being replaced by ActionPlanIt) | In-House | Counseling Student and Learning Services | Educational Planning System [Interfaces to the SIS] |  | 1 | Ellucian DegreeWorks and Banner Native
Endeavor - Library (moving to OCLC WorldShare) | Ex Libris | Primary: Library & students Secondary: All areas | Library System [Interfaces to the SIS] |  | 1 | Interface to OCLC needed?
Endeavor - Media Booking (may be eliminated) | Ex Libris | New Media Center | Media and A/V Materials check-out system |  | 1 | Unknown Status
Eureka | Californaia Information Systems | Job Placement | Career discovery system - Now entirely 3rd party web based |  | 1 | On Hold. Ellucian is working on a state-wide solution with Eureka and Symplicity CMS Dale: stand-alone | No integration. Lincense requires that students connect from PCC network. |  | N | Y | N
Faculty On-line Services |  |  | Grades, Drops, Rosters, and other on-line services |  | 1
Finance | In-House | Primary: Fiscal Services Secondary: All areas | Accounts Payable Accounts Receivable General Ledger |  | 1 | Banner Finance
Financial Aid Management System (FAMS) | Regent | Financial Aid Office Fiscal Services | Scholarships and Financial System Interfaces to EDExpress and Fiscal for financial aid warrants to students [Interfaces to the SIS] |  | 1 | Banner Financal Aid
General Scholarship | Developed In House |  | Home-grown web app for students to submit their application and forward letters of recommendation. Once the application is submitted by the student, Financial Aid reviews and rates the applications at: https://www.pasadena.edu/portal/depts/finaid/scholarship/index.cfm?Mode=Processing&RateType=GS&AcaYear=2012-2013 to review and rate the applications. |  | 1 | Banner FA, BDMS and workflow | No integration. Link from portal with no SSO |  | N | Y | N
Great Plains Dynamics | Microsoft | Student Business Services | Finance System for college’s Auxiliary Services; includes payroll | Applications Group | 1 | Banner Finance | No integration. Desktop client.
GreenTree | GreenTree Sysems | Human Resources | Employment applicant contact and tracking system | Chuck | 1 | Banner Human Resources | Replaced by Talent Management. May want a portlet with SSO from LancerPoint portal.
National Student Clearninghouse "NSLDS" extract - not applicable. This is not an integration issue. However, if we provide SSO from LancerPoint, a connector that passes appropriate credentials will be required. |  | Banner |  |  |  | 3 |  | Standard Banner Student extract job. Need to verify that it has additional elements required for tracking system. | Required monthly, but actually run weekly. | [6 empty] | Phase 2 at earliest.
Hourly Payroll | In-House | Primary: Fiscal Services Secondary: All areas | Hourly payroll for hourly and overload faculty Hourly payroll for unclassified staff [Interfaces to the SIS] [Interfaces to LACOE-HRS via PCCHRS] |  | 1 | Banner Human Resources and Kronos
i1440 Sevis (archived) | International 1440 | International Students Office | System to support mandated international student reporting through SEVIS |  | 1 | Banner Student and Ellucian fsaAtlas
LACOE-RAD | LACOE | Fiscal Services | LACOE electronic reports distribution system |  | 1 | Temporary interface while PCC is Fiscally dependant Dale: standalone with shared storage needs.
LancerLink Online Services to Students |  |  | Registration and other on-line functions | Dale | 1
Learning Centers Systems |  |  | Instructional and Student and Learning Services lab and learning centers usage tracking | Dale | 1
Mainsaver | J. B. Systems | Facilities | Job Ticket and Preventative Maintenance System |  | 1 | Stand-alone
Math Lab Usage Tracking System |  |  | Math instructional lab usage tracking | Bob Lane | 1
Nolij Workflow and Imaging System | Nolij | Financial Aid Office Future: Remainder of Student and Learning Services | Workflow and Imaging System [Interfaces to FAMS] |  | 1 | Functions moving to BDMS and Banner Vendor: Perceptive Software (Kansas) perceptivesoftware.com - they apparently have tight integration with Banner. | Remaining but no integration requirements. Existing content will need to be converted to BDMS. Currently, BDMS is not part of phase 1, so this system will continue to be used stand-alone in the interim.
Online 5 | Escape Technologies | Primary: Purchasing Secondary: All areas | Requisiting Purchasing Warehouse Fixed Assets |  | 1 | Banner Finance
Opto22 EMS | Opto22 | Facilities | Energy management and process control system |  | 1 | Unknown Status
PCCHRS | In-House | Human Resources Payroll MIS Reporting | An extract of the information that the college maintains in the LACOE – HRS; used to drive State MIS reporting, hourly payroll system, staff ID, staff information on and access to web site [Interfaces to LACOE-HRS] | Nelson | 1 | Banner Human Resources | No integration requirements
Purchasing Contracts System | In-House | Purchasing | System to manage the contracts that Purchasing initiates and manages | Dale | 1 | Banner Finance
ReportExec | Competetive Edge | Police and Safety | Police incident tracking and reporting system |  | 1 | Stand-alone
Schooling/3000 Student Records and Instructional Support | CCCSC | All Areas | Provides Student Records and Instructional Support functions e.g. Admissions/Records, Curriculum, Registration, Scheduling, Student Accounts, Student Services, Testing, State MIS, etc) Web Registration Systems (EPOS) PCCharge credit card gateway Other Online Services for Students Other Online Services for Faculty |  | 1 | Replaced by Banner Student
Secure SIS Web Services | In-House | All areas Students | Main college web site Faculty: Instructional information Students: Academic information, transfer information, registration services (including payment of fees), enrollment fee receipts [Has direct access to the SIS] |  | 1 | Luminis Platform
Sequoia On-line Bookstore |  |  | On-line bookstore (bookstore.pasadena.edu) |  | 1 |  | ?
Sequoia Point-of-Sale |  |  | POS system for bookstore |  | 1 |  | ?
Short Term Loans |  |  | Home grown web app for students to apply for the short term book or cash loan at this site. Once the application is submitted, Financial Aid reviews, approves and processes at: https://www.pasadena.edu/portal/depts/finaid/emergency-loan/index.cfm?ResetSearch=1 | web group | 1 | Banner Student and TouchNet | No interface required. Requests will be taken by this system. But it will be input into Banner Student manually as an A/R.
SiteLock | SiteLock | Facilities | Locksmith/key control system for management of keys and lock cylinders |  | 1 | Status Unknown
Student Printing System | CCS | Student labs | Printing charge-back system for students |  | 1 | Status Unknown
TeamHeadquarters | Entry Software | MIS Office | Projects Management System |  | 1 | Status Unknown
teamsites.pasadena.edu | Microsoft SharePoint | All areas | SharePoint system for information collaboration | Dale | 1 | Status Unknown | Potentially SSO?
The Financial Edge (archived) | BlackBaud | Foundation | Finance system for the Foundation |  | 1 | Banner Finance
TLC System | Consultants | TLC Other grant funded areas | Student contact and tracking system Based upon multi-user FileMaker DB [Interfaces to the SIS] | web group | 1 | Status Unknown | TLC is used presently to manage interactions (contacts) with students. BRM's functionality may be used to manage campaigns and interactions with students in place of TLC
WebBoard (limited usage) | Akiva | All Areas Students and faculty | Forums system to enable on-line discussions and information sharing between groups of people; being used in support of classroom activities and various administrative activities, e.g. for ESL classes and the Institutional Planning Process |  | 1 | Luminis Platform
Xerox Auditron System | In-House | Office Services | System to track and charge-back copy machine usage for copiers that are centrally supported by Office Services | Dale | 1 | Status Unknown
AccuTrack Learning Center System | AccuTrack | Languages - ESL Center | System to management and track student activities within the Languages - ESL Center [Interfaces to the SIS] | Jeff Laun | 1 | Unknown Status | ETL | Import into Banner (end of term) Export out of Banner (daily, based on reg changes). |  |  |  | 2013-04-30 | High | 8 | By start of Summer 2013 (end of April 2013) | This product still being assessed for positive attendance tracking. Another solution may be used. Need to provide Jeff with the tables he needs to query from. Antonio can provide. Only used by the ESL lab. To replace this, we need to identify alternative products that best interface with Banner. No recommendation, currently.
Legend | Status Unknown |  |  |  | 0
| Not moving forward with this application |  |  |  | 1
| May not be retained depending upon functionality of AIS and thus not require interfacing |  |  |  | 2
| Retain and integrate with Banner |  |  |  | 3

## New Items
Application System Name | Source | Areas Directly Supported | Functional Desctiption | Point Person | Category | Rick's Comments | Type of Integration | Frequency | SSO? | Link? | Account Dependency | Date Required | When Required? | Notes
Keenan BenefitBridge Software • Feed for benefits/retirement related data not included in BenefitBridge • Feed for benefits/retirement related payments collected that are not included in BenefitBridge • Feed of STRS • Feed of PERS |  |  | Benefits management
New Hire Registry Reporting
Feed of data from LACOE to Banner HR/Finance (required before we can run Payroll in Banner?)
Feed of HR data to LACOE | [13 empty] | We can potentially data integrate from LACOE into ODS and then push a sub-set of data into pseudo-employee recorrds (pre-HR)
Feed of Finance data to LACOE |  |  | Submission of financial data to LACOE | [10 empty] | Vendors and payment warrents are pushed back to LACOE through an existing interface (commerical and FinAid) Check images are not sent to LACOE. Check detail is sent. We basically need to do a check run from Banner without printing/cutting checks. We submit vouchers/vendors to LACOE and LACOE needs to report back what they generated so that we can pull up a check register in Banner. Currently a document ID is sent to LACOE, which is the check number.
Refunds for student financial aid | [13 empty] | 6/26 - Bob Lane working on this extract. Needed for first commercial warrant run (7/12) and student refunds from student AR (refund run for manually for Summer, will need to be automated Fall)
Commercial warrants (Accounts Payable)

## Environments & Utilities
Environment or Utility System Name | Source | Areas Directly Supported | Functional Desctiption
BackPack Maestro Print Services SpoolMate | ROC Software | MIS | HP 3000 Backup System HP 3000 Job Control System HP 3000 Print Services HP 3000 automatic routing of reports to printers
BackupExec | Symantec | MIS | Backup system for legacy MIS servers Backups data to direct attached tape drives
CommVault | CommVault | MIS | Backup system for MIS servers Includes network connected disk2disk unit and tape library for off-site storage preparation
Vesoft MPEX Vesoft Security Vesoft Veaudit | Vesoft | MIS | Utilities to manage the HP3000's databases and access security settings
Vmware Virtual Environment | Vmware | MIS | Virtual environment for servers and desktops